## Sheet2
proposed
Task ID | Task Name | JAN | [23 empty] | FEB
|  | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | 2026-02-01 | 2026-02-02 | 2026-02-03
|  | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday
Section 1 - Identifying and Defining (20 Marks) | bar: 2026-01-08 to 2026-01-20
1 | 1.1 — Client Scenario | bar: 2026-01-08 to 2026-01-10
2 | 1.2 — Environmental Specification | bar: 2026-01-10 to 2026-01-11
3 | 1.3 — List of Objectives | bar: 2026-01-11 to 2026-01-12
4 | 1.4 — Performance Criteria | bar: 2026-01-12 to 2026-01-13
5 | 1.5 — IPO (Input-Process-Output) | bar: 2026-01-13 to 2026-01-14
6 | 1.6 — Gantt Chart | bar: 2026-01-08 to 2026-01-09; 2026-01-25
MILESTONE 1: Stage 1 Complete (Jan 20)
7 | Section 2 - Research and Planning (30 Marks) | bar: 2026-01-21 to 2026-02-03
8 | 2.1 — Research | bar: 2026-01-21 to 2026-01-24
9 | 2.2 — Data Flow Diagram (DFD) | bar: 2026-01-23 to 2026-01-26
10 | 2.3 — Storyboard | bar: 2026-01-25 to 2026-01-28
11 | 2.4 — Pseudocode | bar: 2026-01-27 to 2026-01-30
Actual
Task ID | Task Name | 2026-01-08: JAN
|  | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31
|  | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Section 1 - Identifying and Defining (20 Marks) | bar: 2026-01-08 to 2026-01-20
1 | 1.1 — Client Scenario | 2026-01-12: done 1st draft
2 | 1.2 — Environmental Specification | bar: 2026-01-09 to 2026-01-12
3 | 1.3 — List of Objectives | bar: 2026-01-08 to 2026-01-11
4 | 1.4 — Performance Criteria | 2026-01-12: done 1st draft
5 | 1.5 — IPO (Input-Process-Output)
6 | 1.6 — Gantt Chart | bar: 2026-01-08; 2026-01-25
MILESTONE 1: Stage 1 Complete (Jan 20)
7 | Section 2 - Research and Planning (30 Marks) | bar: 2026-01-21 to 2026-01-31
8 | 2.1 — Research | bar: 2026-01-21 to 2026-01-24
9 | 2.2 — Data Flow Diagram (DFD) | bar: 2026-01-23 to 2026-01-26
10 | 2.3 — Storyboard | bar: 2026-01-25 to 2026-01-28
11 | 2.4 — Pseudocode | bar: 2026-01-27 to 2026-01-30