## Sheet1
L-Plate Logger - HSC Major Project Gantt Chart
Due Date: Tuesday, 21 July 2026
Task ID | Task Name | Duration | W1 26/01 | W2 02/02 | W3 09/02 | W4 16/02 | W5 23/02 | W6 02/03 | W7 09/03 | W8 16/03 | W9 23/03 | W10 30/03 | W11 06/04 | W12 13/04 | W13 20/04 | W14 27/04 | W15 04/05 | W16 11/05 | W17 18/05 | W18 25/05 | W19 01/06 | W20 08/06 | W21 15/06 | W22 22/06 | W23 29/06 | W24 06/07 | W25 13/07 | W26 20/07
1 | SECTION 1: IDENTIFYING & DEFINING | 28
1.1 | Client Scenario Development | 7
1.2 | Environmental Specification | 14
1.3 | List of Objectives (Functional) | 7
1.4 | List of Objectives (Non-Functional) | 7
1.5 | Performance Criteria | 14
1.6 | IPO Charts | 7
1.7 | Gantt Chart Creation | 7
M1 | MILESTONE 1: Section 1 Complete (Week 3) | 7 |  |  | @
2 | SECTION 2: RESEARCH & PLANNING | 35
2.1 | Market & Competitor Research | 14
2.2 | Technology Stack Research | 14
2.3 | Data Flow Diagrams (Login) | 7
2.4 | Data Flow Diagrams (Trip Logging) | 7
2.5 | Data Flow Diagrams (AI Chatbot) | 7
2.6 | Storyboard/Wireframes | 14
2.7 | Pseudocode - Authentication | 7
2.8 | Pseudocode - Trip Processing | 7
2.9 | Pseudocode - Parent Approval | 7
M2 | MILESTONE 2: Section 2 Complete (Week 6) | 7 | [7 empty] | @
3 | SECTION 3: DEVELOPMENT & PRODUCTION | 98
3.1 | Backend Setup (Flask/SQLite) | 14
3.2 | User Authentication System | 14
3.3 | Database Schema Implementation | 14
3.4 | ESP32 Firmware - GPS Module | 14
3.5 | ESP32 Firmware - Accelerometer | 14
3.6 | ESP32 Firmware - SD Card Logging | 14
3.7 | Trip Upload API Endpoints | 14
3.8 | React Frontend - Logger Interface | 21
3.9 | React Frontend - Dashboard | 14
3.10 | Parent Approval Workflow | 14
3.11 | PWA Implementation (Service Workers) | 14
3.12 | AI Chatbot - RAG Setup | 14
3.13 | AI Chatbot - NSW Laws Integration | 14
3.14 | Day/Night Hour Tracking | 7
3.15 | Progress Visualisation Charts | 14
3.16 | Logbook Maintenance | 98
3.17 | Version Control (Git) | 98
M3 | MILESTONE 3: Development Complete (Week 22) | 7 | [21 empty] | @
4 | SECTION 4: TESTING & MAINTAINING | 35
4.1 | Acceptance Testing | 14
4.2 | Load Testing | 14
4.3 | User Survey Design | 7
4.4 | User Survey Distribution | 14
4.5 | Bug Fixes & Refinements | 14
4.6 | Video Demonstration | 14
4.7 | Final Documentation Review | 7
M4 | MILESTONE 4: PROJECT DUE (21 July 2026) | 7 | [25 empty] | @
LEGEND:
Section 1: Identifying & Defining
Section 2: Research & Planning
Section 3: Development & Production
Section 4: Testing & Maintaining
Milestone