## Sheet1
Milestone | Notes | Task Name | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27
Project start | Brainstorm ideas, plan schedule | Project Planning | bar: 2025-06-01 to 2025-06-03
Begin coding | Clone base game, test setup, learn the code base | Setup GitHub & Scaffold Code | bar: 2025-06-02 to 2025-06-04
NPC feature complete | Shop implementation make a invotory calss and some use buffs | NPC Interaction Implementation | bar: 2025-06-04 to 2025-06-11
Orc functional compleate | Design use enemy but change the stats and skin | New Enemy (Orc) Implementation | bar: 2025-06-09 to 2025-06-15
Item added | Design make a Orc drop item that is a power up and uses the invotory | New Item(s) Implementation | bar: 2025-06-14 to 2025-06-21
Game is free from magjor bugs | Playtest, fix broken features, tune for difficay but need to be compatible | Testing and Bug Fixing | bar: 2025-06-20 to 2025-06-25
DFD 0 complete | System-external interaction | DFD Level 0 Creation | bar: 2025-06-23 to 2025-06-26
DFD 1 complete | Data flow for character.py | DFD Level 1 Creation | bar: 2025-06-23 to 2025-06-26
Class diagram done | Show inheritance and polymorphism | Class Diagram Creation | bar: 2025-06-23 to 2025-06-26
Log up-to-date | Use the Git time machine to review commits and make a good logbook. | Logbook Updates | 2025-06-23: I actually started on the 23 june
Game ready | Polish code, check requirements, update the docs | Final Testing & Polishing | bar: 2025-06-23 to 2025-06-26
make notes | Use voice-to-text to get to ideas down fast, then get ChatGPT to correct the errors so I can reference it to help me make the video. | Make notes about how each feature was implemented to help write the video script. | bar: 2025-06-04 to 2025-06-25
planing doument for video | Draft explanation points | Video Walkthrough Planning | bar: 2025-06-25 to 2025-06-26
Final video exported | Ensure it fits 4-minute limit | Record & Edit Video | bar: 2025-06-26
Assessment submitted | Upload files and video make sure that the git I submitted final spell check | Final Submission | bar: 2025-06-27